## Sheet1
Sr.No. | Points | Zing Action | Remarks
1 | Punch in punch out to inform all employees. (Ebru Amar) // Training Zing | Yes | Ensure all employees card code mapping with PI as YES is done from 1-Apr-2024 | Done. Ranveer
2 | Week off - Sat & Sun for UAE and Turkey, Saudi and Near East – Friday and Saturday. Zing Team 15.04.2024 | Yes | Update the attendance rule group for employees and their week-offs from Calendar Setup | Done. Ranveer
3 | Set welcome message. (Ebru Amar) Ebru 05.04.2024 | No | Follow Up with Amar/Ebru on it
4 | Check the time zone for attendance. Zing Team 15.04.2024 | Yes | JIRA to set time zone as per country | Rohan to action
5 | Father name to be made non mandatory. Zing Team 15.04.2024 | Yes | ED and EC configuration (all roles)
6 | Probation for Turkey 2 months, check for all regions as per list shared previously. Zing Team 15.04.2024 | Yes | Check and set calendar group wise probation and notice period | Rohan to action
7 | Check with Divya with regards to integration HR connect / Zing HR (Ebru Amar) Amar 05.04.2024 | No
8 | Added new employee and check if comes in Turkey – Send new employee updated list to Zing. 05.04.2024 | Yes | Pending from WIKA | Rohan to action
9 | Travel request to be created. Show visibility. Zing Team 20.04.2024 | Yes | Pending from WIKA | Rohan to action
10 | Meals and travel allowance limit to be set. 05.04.2024 | Yes | Pending from WIKA | Rohan to action
11 | Taxi place to place to be activate. Zing Team 15.04.2024 | Yes | Claims configuration | Rohan to action
12 | Drop down of currency, Currency to be captured in Expense form. Zing Team 20.04.2024 | Yes | Create a drop down of currency | Rohan to action
13 | Travel request - capture requisition Id and this talks to the expense request. Linked to Nr9 . Zing Team 20.04.2024 | Yes | Need to check feasibility | Rohan to action
14 | Session time out to be checked for longer period. . Zing Team 20.04.2024 | No | No Action
15 | Expense claims - to be listed under one tab unlike the multiple tabs we have setup - to be discussed (Ebru, Amar, Finance Team) / discussed Amar will send mail today | No | Pending from WIKA
16 | Prefix the Category in the subcategory - TBD / Separate discussion on Periderm. discussed Amar will send mail today related to Point 15 | No | Pending from WIKA
17 | Check direct report 18.05.2024 | Yes | Enable reportees check in reports | SEM, LBD, Attendance, etc
18 | Birthday leave Turkey to be added. . Zing Team 20.04.2024 | Yes | Create a birthday leave for Turkey leave group | Done. Ranveer
19 | Access to approve for all employees to Ebru and Amar on behalf of everybody Zing Team 20.04.2024 | Yes | Provide switch user access to Amar and Ebru - Leave application on-behalf | Done. Ranveer
20 | Review social tab to categorize WIKA Team 20.04.2024 | No | Pending from WIKA
21 | We will give access to only limited team for Social area, management team and Hr Team – Details to be shared by WIKA before 05.04.2024 | No | Pending from WIKA
22 | Spouse name instead of Husband name Zing Team 20.04.2024 | Yes | Rename Husband name to spouse name in ED for all roles | Done. Ranveer
23 | Send excel file with new employee details added and left and salary details – To be shared with Zing. WIKA Team 05.05.2024 | No | Pending from WIKA
24 | Allow employees to update passport detials, information. ESS access will be given for passport details entry and educational details as well. Zing Team 20.04.2024 | Yes | Setup ID Proof and Skills and Qualification section for all roles. National ID, Passport, Driving Lisensce | Done. Ranveer
25 | Add languages in drop down menu Turkish, Arabic, Egyptian etc Zing Team 20.04.2024 | Yes | Add languages from ED template - Raise JIRA to add Language | Rohan to action
26 | Documents – Add job description, wfh policy for acknowledgement. WIKA Team 20.04.2024 | No | Pending from WIKA
27 | Annual leave balance of TR will be shared with Zing HR- Ebru 05.04.2024 | Yes | Pending from WIKA
28 | Near East leave management will be checked with Arwa – Amar 18.04.2024 | No | Pending from WIKA
29 | Check policies and maintain in the system WIKA Team 20.04.2024 | No | Pending from WIKA