## Open Points
Sl.No | Stage | Module | Observation | Date Reported | Reported by | Impact ( Company or group) | Priority | Ownership | WJT Comments | ZingHR Response | Status | WJT Comments post checking | Status as on 30 Nov | ZingHR Status 29-Oct | Remarks | 13-Nov ZingHR | 2023-12-03 | Next Actor | Status-Legends
14 | Soft Launch | Employee creation | During onboarding - Education qualification , Address input,employment history, family details entry | [7 empty] | To be revisited later | Option given to upload by employee or bulk |  |  | This feature is available with Recruitment where candidate once confirmed fills his/her personal details and flows to the employee master | With Recruitment
20 | UAT | Core HR- Employee master | Recruitment charges captured under Employee master creation- Same has to be deducted or waived if someone gets seperated within first 2 years of contract | [5 empty] | Formula-value/(number of days in the year*2)*number of remaining days |  | To be revisited later | Confirmed that provision will be set during Recruitment module goes live |  | To be discussed further | will come in recruitment module - to belinked to payroll module | With Payroll
21 | UAT | Core HR- Employee master | Relocation charges plus years of deduction -Same has to be deducted or waived if someone gets seperated within first 2 years of contract | [5 empty] | Formula-value/(number of days in the year*2)*number of remaining days |  | To be revisited later | Confirmed that provision will be set during Recruitment module goes live |  | To be discussed further | will come in recruitment module - to belinked to payroll module | With Payroll
22 | UAT | Core HR- Employee master | Joining Bonus plus years of deduction -Same has to be deducted or waived if someone gets seperated within first 2 years of contract | [5 empty] | Formula-value/(number of days in the year*2)*number of remaining days |  | To be revisited later | Confirmed that provision will be set during Recruitment module goes live |  | To be discussed further | will come in recruitment module - to belinked to payroll module | With Payroll
24 | UAT | Core HR | Frequency of alerts for expiry dates to be set (Visa and passport) | [5 empty] | Alert to go out to HR/ legal spoc 1 month before expiry of Visa and Passport |  | Work In Progress | WJT to Test | WJT to Test | Not closed | Reminder has been set for 30 days as requested to the employee on email |  | Pending. Santhosh VISA expiry on 10-Jan-2024. HR to be notified need to be checked with internal team
25 | UAT | Core HR | Alert for Expiry of family members visa and passports. | [5 empty] | Alert to go out to HR/ legal spoc 1 month before expiry of Visa and Passport |  | Development - Under customisation | Should be develped as we will be storing family id proofs | 2024-02-24 |  |  | Dev
26 | UAT | Core HR | Emp code series to be finalized for each company to fix the auto generation | [5 empty] | Intial 2 months data will be entered in both systems post which series have tobe set in Zing Hr for continuationof Emp codes. |  | To be revisited later | Will be inprogress untill the series is finalized from WJ Towell end prior to payroll go live | 2023-01-24 | To be discussed further | To be done after payroll Go Live when ZingHR is the primary source for employee creation | At Go Live
27 | UAT | Core HR | Asset tagging against employee to be created | [5 empty] | separate development - IT requirement | Asset can be tagged to employee | Development - Under customisation | Fields to be provided in payroll for report purpose so that employee assets such as Cars, Accommodation can be tracked | 2023-12-24 |  | Zing to check for Company Asset tagging in profile and check for report | Dev | Check for the Company Asset option in the profile | Doesn’t work - checking with Hozafa
32 | UAT | Attendance& leave | Public holiday leave adjustment - Auto adjustment | [5 empty] | Set up to be done for system to Credit back public holidays if it is at the start or end of annual leave |  | Development - Under customisation | Need to know the status as it will be part of Core HR Go live | 2023-12-24 |  | Zing to check on UAT and update | Nov | Rohan to test and update | Doesn’t work - checking with Hozafa
33 | UAT | Attendance& leave | Grade chosen as JM1 and if leave Group selected as oman expat 35 - Is there a validation | [5 empty] | Validation of leave balance eligibility as per grade to be system driven | It will be auto-assigned | Work In Progress | Need to cross check while we create employee in that Grade | Closed | Closed | HR to select the correct Leave group - ZingHR will explore options |  | Rohan to update by Monday on this
34 | UAT | Attendance& leave | Delegation of Authority while on leave | [5 empty] | Managers and all admin tagged emps to have otion to delegate their authorty in ZingHr system to replacements when on leave |  | Development - Under customisation | Need to know the status as it will be part of Core HR Go live | 2023-12-23 |  | Expected delivery in Q1'24 | Nov |  | Check with Hozafa
35 | UAT | Attendance& leave | Biometric integration - attendance to reflect before 9:00 AM in Zing HR | [5 empty] | all attandance to be captured live in the system |  | To be revisited later |  |  | WIP | After Attendance integration | This will be done after Attendance integration.
42 | UAT | Attendance& leave | Link the bereavement leave type to show the balance against each transaction- restriction by law | [5 empty] | restriction on leave days by type of demise leave to be set |  | Development - Under customisation |  | 2024-02-01 |  | Expected delivery in Q1'24 | Dev
48 | UAT | Core HR- Employee master | Drop downs for Family visa / Ticket / Medical Insurance - Self, Self & Spouse, Self Spouse and 1 child,Self Spouse and 2 children, Self Spouse and 3 children | [7 empty] | Development - Under customisation |  | 2024-03-01 | Customisation | Expected delivery in Q1'24 | Dev
52 | UAT | Core HR | Employee search by role/designation or company | [7 empty] | TBD |  | Devlopment will be revisited later | Customisation-P3 | Expected delivery in Q1'24 | Dev
58 | UAT | Attendance& leave | Feasibility to check either CO or OT - for a same employee and system to accmulate extra hours worked for a week and decision to pay either comp off or OT | [7 empty] | Development - Under customisation |  | 2023-12-23 | Development - Under customisation | Time Accumulation - Testing under progress. Zing to check and update by next week | Dev |  | To be tested
77 | UAE UAT | Employee Database | 4.Too many fields with regards to company, sub company, division/ department | [7 empty] | Work In Progress | Post cost center and attribute code mapping the coupling activity to be done | Attribute master codes | closed | Anbu to share which attribute needs to be disabled and not required in the employee creation form. Also, share coupling of any new attribute unit created and needs to be coupled
85 | UAE UAT | Others | 7 Passport Release - we were not shown passport release as a process - as we keep passports with us. | [7 empty] | Development - Under customisation | Is there a workflow or module to do the same - New workflow module to be developed - Zing HR to develop (P1) | 2023-12-23 | Pendig Zingh -P1 | Form/Workflow - To be set and test on UAT. Anbu to send fields required in the form and the workflow details | ZingHR to setup |  | Workflow Form
86 | Soft Launch | Attendance | Overtime override option to be checked- If a manager feels that some one has clocked extra hours Can the manager or HR or Payroll edit the overtim hours of an employee | [5 empty] | TO/Payroll spoc should be able to edit overtime hours clocked for payroll processing |  | Development - Under customisation |  | 2023-12-23 | WIP | OT hours to change for payroll processing, input upload | ZingHR to setup - Dec
90 | Soft Launch | Attendance View | Head of a company or division or HR of the cluster should have a view option that they should be able to see 1 day attendance of all the employees under their division or company or attribute wise selection with punch in and out details. If it is a devlopment or customization require please initiate the same | [7 empty] | Development - Under customisation | Zinghr to Cross check in Time office view and confirm | Zinghr to Cross check in Time office view and confirm |  | Power BI report for attendance to be enabled | Report view to be explored
97 | Soft Launch | Shift & Roster | Break shift option to be configured and require discussion about the same | [6 empty] | 12 hours shift and OT will start calculating 30 mins post 12 Hours | Development - Under customisation | Clubbed with Shift details to be shared as final | 2023-01-24 | Pendig WJT | In ther interim, ZingHR to check for solution. As of now, flexi shift can be assigned to such employees | Explore new release
100 | Soft Launch | Help Desk | Employee letters will be a catergory and sub type of different letters to be configured | [7 empty] | Work In Progress | Letter templates and categories to be shared by WJT | WJT to Share | WIP | Letter templates and categories to be shared by WJT | Pending data from WJT
101 | Soft Launch | LG Module | Letter formats to be finalized and created in the module and auto generation of letters to be done from particular fields in the system eg (name, designation, DOJ, Salary information) | [7 empty] | Work In Progress | Letter templates and categories to be shared by WJT | WJT to share | WIP | Letter templates and categories to be shared by WJT | Pending data from WJT
102 | Soft Launch | Shift & Roster | Require a provision to view and assign the shifts for those in only in a particular department or cluster (Attribute wise) Eg by country, Business cluster. | [7 empty] | To be revisited later |  | To be revisited post the biomteric integration and key use training output |  | To be checked by Zing HR | ZingHR to setup
106 | Soft Launch | Employee profile | Following fields are to be enabled for family member details and doesn’t need to be marked as Mandatory fields while updating. Similarly which template to be downlaoded for bulk upload of all these fields ? 1.Passport Number 2. Place of Issue 3.Passport Issued date 4. Passport Expiry Date 5. Civil or Emirates ID Number 6. Civil or Emirates Id Issued date 7. Civil or Emirates Id Expiry Date 8. Visa Number 9. Visa Expiry date 9. UID Number - for family members | [7 empty] | Development - Under customisation |  | 2024-03-01 |  | Expected delivery in Q1'24 | DEV
110 | Soft Launch | Duty Resumption | Duty resumption from Annual leave should be activated and demo to be shown | [7 empty] | Development - Under customisation |  | 2024-03-01 |  | Under development | ZingHR to setup
121 | Soft Launch | Employee Creation | Old employee code should be allowed without validation till payroll goes live | [7 empty] | Work In Progress |  |  |  | To be checked by ZingHR